## Backlog Report
Mancala
Theme | ID | User Story | Acceptance Criteria | Comments | Sprint | Status | Points
Making the game | MTG1 | Make a title screen | a) Start button transitions to game screen, acceptable graphics |  | Sprint 1 | Accepted | 3.0
| MTG2 | Make a game screen | a) Acceptable graphics | Bonus: Moving pieces | Sprint 1 | Accepted | 8.0
| MTG3 | Make an ending screen | a) Create acceptable graphics and possible restart button |  | Sprint 1 | Accepted | 3.0
| MTG4 | Research mancala game and rules | a) Basic understand of game rules |  | Sprint 1 | Accepted | 1.0
| MTG5 | have smooth player interaction | a) Working functionality within the buttons |  | Sprint 2 | Accepted | 8.0
| MTG6 | create a data structure to represent the game | a) Use of a data structure that represents the game board and storage | 2-D array of integers to represent the number of seeds in each pot. Need to find an effective way of representing stores. | Sprint 1 | Accepted | 1.0
| MTG7 | create functions for the data structure | a) Create a move function that moves seeds across the data structure representing the game board | move(index,index), will most likely be in the player object | Sprint 1 | Accepted | 4.0
| MTG8 | make a function that checks for end state | a) the check end state function correctly identifies the end state | Create an if statement to check if storage+storage=number of seeds | Sprint 1 | Accepted | 3.0
| MTG9 | create a game manager | a) Create a finite state machine to represent game screens and which functions go in which states | Need to identify extra functions that may be needed in the game manager. | Sprint 1 | Accepted | 4.0
| MTG10 | research a GUI that is most effective for this particular project | a) Unanimous agreement on GUI. | Options include : netbeans, java swing, etc | Sprint 1 | Accepted | 1.0
| MTG11 | create a player object | a) Create a boolean to represent player one or two, player score, bool to check turns. | Boolean values represent the player turns and object contains each players score. | Sprint 2 | Accepted | 1.0
| MTG12 | create a function for the player to move pieces | a) Make player call move function in data structure and validate that a player is only moving his own pieces. | Most likely inside the player object. Player should be restricted to not be able to take the others players pieces. | Sprint 1 | Accepted | 5.0
| MTG13 | Make a turn indicator | a) Create acceptable graphics that indicate which players turn it is during the game. | Could be a banner, a symbol, etc. | Sprint 2 | Accepted | 2.0
| MTG14 | create unit tests | a) Test the move function in the data structure, test game manager to ensure correct transition of states. | Tests should be comprehensive when first written, however can be altered as development continues to ensure a complete working project. | Sprint 1 | Accepted | 6.0
| MTG16 | Vary number of seeds in hole & random distribution of seeds | Player one and player two should mirror eachother |  | Sprint 2 | Accepted | 2
| MTG17 | Implement a time limit | if player does not make move within time limit, they lose |  | Sprint 2 | Accepted | 3
| MTG18 | Implement "Pie Rule" | only happens on second move, follows class document |  | Sprint 2 | Accepted | 4
| MTG19 | Edit Start for input on variable game hole | Allows user to input how many holes they want |  | Sprint 2 | Accepted | 3
| MTG20 | Edit game Screen for variable game holes | Draws the gameScreen according to user input |  | Sprint 2 | Accepted | 1
| MTG21 | Variable game board holes | Edits the board class accoring to user input |  | Sprint 2 | Accepted | 3
| MTG22 | Insert ending screen into game screen | Shows a more accurate ending screen |  | Sprint 2 | Accepted | 4
| MTG15 | keep up code styling, comments and documentation | a) Doxygen files, consistent naming/commenting. |  | Sprint 1 | Accepted | 4.0
| Total for theme 'Making the game' |  |  | 74
Creating AI | CRA1 | research a tree data structure in java | a) Get the tree data structure to compile with arbitrary data. |  | Sprint 1 | Accepted | 1.0
| CRA2 | research optimal ways to play the game | a) Read at least one article about mancala and write a one paragraph summary to update the other team members |  | Sprint 1 | Accepted | 2.0
| CRA3 | implement a minimax tree | a) Pass unit tests. |  | Sprint 2 | Accepted | 7.0
| CRA6 | decide an approach for the utility function | a) Use research to decide if we want to use greedy, random, or other algorithms to implement utility function. |  | Sprint 1 | Accepted | 9.0
| CRA7 | implement the utility function | a) Create DFS for any given tree and return maximal points path. |  | Sprint 2 | Accepted | 4.0
| CRA8 | implement alpha beta data pruning on one level | a) Make sure the degrees of the parent is less after pruning and make sure it prunes non optimal local moves. |  | Sprint 2 | Accepted | 7.0
| CRA9 | Implement alpha beta data pruning on multiple levels | a) Make sure the degrees of the parent is less after pruning and make sure it prunes non optimal global moves. |  | Sprint 3 | To do | 9.0
| CRA10 | create unit tests | a) Make sure DFS returns correct path, make sure AI has all possible moves, make sure pruning works, make sure computer selects optimal move |  | Sprint 2 | Accepted | 6.0
| CRA11 | keep up code styling, comments and documentation for AI | a) Doxygen files, consistent naming/commenting. |  | Sprint 3 | To do | 4.0
| Total for theme 'Creating AI' |  |  | 57.0 points
| CS14 | make a timing function | a) Research a timing library to use. |  | Sprint 2 | Accepted | 1.0
| CS15 | keep up code styling, comments and documentation for the network | a) Doxygen files, consistent naming/commenting. |  | Sprint 3 | To do | 4.0
| CS16 | Create Unit Tests | a) Make sure the input/output is what's expected at each end point. |  | Sprint 3 | To do | 4.0
| CS17 | Make a Basic Client server Model to that we can build on throughout the project | Simulates the one in class with more functionality according to our needs |  | Sprint 2 | Accepted | 4
| Total for theme 'Client Server Model' |  |  | 11.0 points
Other | OTH1 | Write Group Report | a) Follows MLA format and instructions. |  | Sprint 3 | To do | 1.0
| OTH2 | Decide on Team Manager | a) Decide on team manager by 3/9/2017 |  | Sprint 1 | Accepted | 1.0
| OTH3 | have a team meeting outside of class for Sprint 1 | a) Meet on 3/19/2017 |  | Sprint 1 | Accepted | 1.0
| OTH4 | have a team meeting outside of class for Sprint 2 | a) Meet On 3/26/2017 |  | Sprint 2 | Accepted | 1.0
| OTH5 | have a team meeting outside of class for Sprint 3 | a) Meet 4/2/2017 |  | Sprint 3 | To do | 1.0
| OTH6 | set up project environment | a) Create github, get eclipse/netbeans, compile hello world, and set up text documents. |  | Sprint 1 | Accepted | 1.0
| Total for theme 'Other' |  |  | 6.0 points
Additions | ADD1 | create pi rule button on game screen | pi rule button correctly shows pi rule |  | Sprint 3 | To do | 3
| ADD2 | enhance graphics | lowest priority, make it look cool |  | Sprint 3 | To do | 2
| ADD3 | put in all options for games | options accurately create board as needed, random seeds |  | Sprint 3 | To do | 7
| ADD4 | implement random seeding | seeds are distributed in a "random" fashion on board start |  | Sprint 3 | To do | 2
| ADD5 | fix start screen (have start game start the game) | buttons are less confusing for suers |  | Sprint 3 | To do | 2
| ADD6 | Implement all server functions | pass testing |  | Sprint 3 | To do | 10
| ADD7 | implement all client functions | pass testing |  | Sprint 3 | To do | 10
| ADD8 | connect AI to server | can create an AI player through server |  | Sprint 3 | To do | 5
| ADD9 | Have AI recognize pi rule | pass unit tests |  | Sprint 3 | To do | 3
| ADD10 | Debug Code | Finish all bug fixes on bug list |  | Sprint 3 | To do | 4
| Total for theme 'Other' |  |  | 42 point
Total for backlog 'Mancala' |  |  |  | 202.0 points

## Story List
Theme | ID | User Story | Acceptance Criteria | Comments | Sprint | Status | Points
Making the game | MTG1 | have a title screen | a) Start button transitions to game screen, acceptable graphics |  | Sprint 1 | Accepted | 3.0
Making the game | MTG2 | have a game screen | a) Acceptable graphics | Bonus: Moving pieces | Sprint 1 | Accepted | 8.0
Making the game | MTG3 | have an ending screen | a) Create acceptable graphics and possible restart button |  | Sprint 1 | Accepted | 3.0
Making the game | MTG4 | Research mancala game and rules | a) Basic understand of game rules |  | Sprint 1 | Accepted | 1.0
Making the game | MTG5 | have smooth player interaction | a) Working functionality within the buttons |  | Sprint 2 | Accepted | 8.0
Making the game | MTG6 | create a data structure to represent the game | a) Use of a data structure that represents the game board and storage | 2-D array of integers to represent the number of seeds in each pot. Need to find an effective way of representing stores. | Sprint 1 | Accepted | 1.0
Making the game | MTG7 | create functions for the data structure | a) Create a move function that moves seeds across the data structure representing the game board | move(index,index), will most likely be in the player object | Sprint 1 | Accepted | 4.0
Making the game | MTG8 | make a function that checks for end state | a) the check end state function correctly identifies the end state | Create an if statement to check if storage+storage=number of seeds | Sprint 1 | Accepted | 3.0
Making the game | MTG9 | create a game manager | a) Create a finite state machine to represent game screens and which functions go in which states | Need to identify extra functions that may be needed in the game manager. | Sprint 1 | Accepted | 4.0
Making the game | MTG10 | research a GUI that is most effective for this particular project | a) Unanimous agreement on GUI. | Options include : netbeans, java swing, etc | Sprint 1 | Accepted | 1.0
Making the game | MTG11 | limit where a player can click | a) Create a boolean to represent player one or two, player score, bool to check turns. | Boolean values represent the player turns and object contains each players score. | Sprint 2 | Accepted | 1.0
Making the game | MTG12 | create a function for the player to move pieces | a) Make player call move function in data structure and validate that a player is only moving his own pieces. | Most likely inside the player object. Player should be restricted to not be able to take the others players pieces. | Sprint 1 | Accepted | 5.0
Making the game | MTG13 | make a turn indicator | a) Create acceptable graphics that indicate which players turn it is during the game. | Could be a banner, a symbol, etc. | Sprint 2 | Accepted | 2.0
Making the game | MTG14 | create unit tests | a) Test the move function in the data structure, test game manager to ensure correct transition of states. | Tests should be comprehensive when first written, however can be altered as development continues to ensure a complete working project. | Sprint 1 | Accepted | 6.0
Making the game | MTG15 | keep up code styling, comments and documentation | a) Doxygen files, consistent naming/commenting. |  | Sprint 1 | Accepted | 4.0
Making the game | MTG16 | Vary number of seeds in hole & random distribution of seeds | Player one and player two should mirror eachother |  | Sprint 2 | Accepted | 2
Making the Game | MTG17 | Implement a time limit | if player does not make move within time limit, they lose |  | Sprint 2 | Accepted | 3
Making the game | MTG18 | Implement "Pie Rule" | only happens on second move, follows class document |  | Sprint 2 | Accepted | 4
Making the game | MTG19 | Edit Start for input on variable game hole | Allows user to input how many holes they want |  | Sprint 2 | Accepted | 3
Making the game | MTG20 | Edit game Screen for variable game holes | Draws the gameScreen according to user input |  | Sprint 2 | Accepted | 1
Making the game | MTG21 | Variable game board holes | Edits the board class accoring to user input |  | Sprint 2 | Accepted | 3
Making the game | MTG22 | Insert ending screen into game screen | Shows a more accurate ending screen |  | Sprint 2 | Accepted | 4
Creating AI | CRA1 | research a tree data structure in java | a) Get the tree data structure to compile with arbitrary data. |  | Sprint 1 | Accepted | 1.0
Creating AI | CRA2 | research optimal ways to play the game | a) Read at least one article about mancala and write a one paragraph summary to update the other team members |  | Sprint 1 | Accepted | 2.0
Creating AI | CRA3 | implement a minimax tree | a) Pass unit tests. |  | Sprint 2 | Accepted | 7.0
Creating AI | CRA6 | decide an approach for the utility function | a) Use research to decide if we want to use greedy, random, or other algorithms to implement utility function. |  | Sprint 1 | Accepted | 9.0
Creating AI | CRA7 | implement the utility function | a) Create DFS for any given tree and return maximal points path. |  | Sprint 2 | Accepted | 4.0
Creating AI | CRA8 | implement alpha beta data pruning on one level | a) Make sure the degrees of the parent is less after pruning and make sure it prunes non optimal local moves. |  | Sprint 2 | Accepted | 7.0
Creating AI | CRA9 | Implement alpha beta data pruning on multiple levels | a) Make sure the degrees of the parent is less after pruning and make sure it prunes non optimal global moves. |  | Sprint 3 | To do | 9.0
Creating AI | CRA10 | create unit tests | a) Make sure DFS returns correct path, make sure AI has all possible moves, make sure pruning works, make sure computer selects optimal move |  | Sprint 2 | Accepted | 6.0
Creating AI | CRA11 | keep up code styling, comments and documentation for AI | a) Doxygen files, consistent naming/commenting. |  | Sprint 2 | Accepted | 4.0
Client Server Model | CS14 | make a timing function | a) Research a timing library to use. |  | Sprint 2 | Accepted | 1.0
Client Server Model | CS15 | keep up code styling, comments and documentation for the network | a) Doxygen files, consistent naming/commenting. |  | Sprint 3 | To do | 4.0
Client Server Model | CS16 | Create Unit Tests | a) Make sure the input/output is what's expected at each end point. |  | Sprint 3 | To do | 4.0
Client Serve Model | CS17 | Make a Basic Client server Model to that we can build on throughout the project | Simulates the one in class with more functionality according to our needs |  | Sprint 2 | Accepted | 4
Other | OTH1 | Write Group Report | a) Follows MLA format and instructions. |  | Sprint 3 | To do | 1.0
Other | OTH2 | Decide on Team Manager | a) Decide on team manager by 3/9/2017 |  | Sprint 1 | Accepted | 1.0
Other | OTH3 | have a team meeting outside of class for Sprint 1 | a) Meet on 3/19/2017 |  | Sprint 1 | Accepted | 1.0
Other | OTH4 | have a team meeting outside of class for Sprint 2 | a) Meet On 3/26/2017 |  | Sprint 2 | Accepted | 1.0
Other | OTH5 | have a team meeting outside of class for Sprint 3 | a) Meet 4/2/2017 |  | Sprint 3 | To do | 1.0
Other | OTH6 | set up project environment | a) Create github, get eclipse/netbeans, compile hello world, and set up text documents. |  | Sprint 1 | Accepted | 1.0
Additions | ADD1 | create pi rule button on game screen | pi rule button correctly shows pi rule |  | Sprint 3 | To do | 3
Additions | ADD2 | enhance graphics | lowest priority, make it look cool |  | Sprint 3 | To do | 2
Additions | ADD3 | put in all options for games | options accurately create board as needed, random seeds |  | Sprint 3 | To do | 2
Additions | ADD4 | implement random seeding | seeds are distributed in a "random" fashion on board start |  | Sprint 3 | To do | 2
Additions | ADD5 | fix start screen (have start game start the game) | buttons are less confusing for suers |  | Sprint 3 | To do | 2
Additions | ADD6 | Implement all server functions | pass testing |  | Sprint 3 | To do | 7
Additions | ADD7 | implement all client functions | pass testing |  | Sprint 3 | To do | 7
Additions | ADD8 | connect AI to server | can create an AI player through server |  | Sprint 3 | To do | 5
Additions | ADD9 | Have AI recognize pi rule | pass unit tests |  | Sprint 3 | To do | 3
Additions | ADD10 | minor bug fixes | All bugs on the "bug list" are fixed |  | Sprint 3 | To do | 4

## Sprint 1
Mancala Sprint 1
Theme | ID | User Story | Acceptance Criteria | Comments | Sprint | Status | Points | Assigned | Date Finished
Creating AI | CRA1 | As the AI developer I want to research a tree data structure in java So I can have a better idea on how to implement a tree data structure | a) Get the tree data structure to compile with arbitrary data. |  | Sprint 1 | Accepted | 1 | Kerry | 2020-03-18
Creating AI | CRA2 | As the AI developer I want to research optimal ways to play the game So I can understand how the computer should be "thinking" before building the AI | a) Read at least one article about mancala and write a one paragraph summary to update the other team members |  | Sprint 1 | Accepted | 2 | Allison | 2017-03-16
Creating AI | CRA6 | As the AI developer I want to decide an approach for the utility function So I can use the most effective algorithm when implementing the utility function | a) Use research to decide if we want to use greedy, random, or other algorithms to implement utility function. |  | Sprint 1 | Accepted | 3 | Allison | 2017-03-19
Other | OTH3 | As a team member I want to have a team meeting outside of class for Sprint 1 So I can have continuous updates on the status of the project | a) Meet on 3/19/2017 |  | Sprint 1 | Accepted | 1 | All | 2017-03-19
Other | OTH2 | As a team member I want to Decide on Team Manager So I can meet the criteria for sprint 1 | a) Decide on team manager by 3/9/2017 |  | Sprint 1 | Accepted | 1 | All | 2017-03-10
Other | OTH6 | As a team member I want to set up project environment So I can be fully ready to start the project | a) Create github, get eclipse/netbeans, compile hello world, and set up text documents. |  | Sprint 1 | Accepted | 3 | All | 2017-03-11
Making the game | MTG4 | As the game creator I want to Research mancala game and rules So I can have a better understanding of the game | a) Basic understanding of game rules |  | Sprint 1 | Accepted | 1 | Kerry | 2017-03-12
Making the game | MTG1 | As the game user I want to have a title screen So I can easily start the game | a) Start button transitions to game screen, acceptable graphics |  | Sprint 1 | Accepted | 3 | Allison | 2017-03-15
Making the game | MTG6 | As the game creator I want to create a data structure to represent the game So I can easily represent the game board behind the scenes | a) Use of a data structure that represents the game board and storage | 2-D array of integers to represent the number of seeds in each pot. Need to find an effective way of representing stores. | Sprint 1 | Accepted | 1 | Kerry | 2017-03-12
Making the game | MTG7 | As the game creator I want to create functions for the data structure So I can effectively represent game moves on the game board behind the scenes | a) Create a move function that moves seeds across the data structure representing the game board | move(index,index), will most likely be in the player object | Sprint 1 | Accepted | 4 | Kerry | 2017-03-12
Making the game | MTG8 | As the game creator I want to make a function that checks for end state So I can move the the ending game screen when the game is over | a) the check end state function correctly identifies the end state | Create an if statement to check if storage+storage=number of seeds | Sprint 1 | Accepted | 3 | Kerry | 2017-03-17
Making the game | MTG14 | As the game creator I want to create unit tests So I can write code geared towards test-driven development | a) Test the move function in the data structure, test game manager to ensure correct transition of states. | Tests should be comprehensive when first written, however can be altered as development continues to ensure a complete working project. | Sprint 1 | Accepted | 6 | Kerry | 2017-03-13
Making the game | MTG15 | As a team member I want to keep up code styling, comments and documentation So I can fill in my portions of code into the project with ease. | a) Doxygen files, consistent naming/commenting. |  | Sprint 1 | Accepted | 4 | Kerry | 2017-03-13
Making the game | MTG9 | As the game creator I want to create a game manager So I can smoothly transition between screens of the game | a) Create a finite state machine to represent game screens and which functions go in which states | Need to identify extra functions that may be needed in the game manager. | Sprint 1 | Accepted | 4 | Rachel | 2017-03-19
Making the game | MTG10 | As the game creator I want to research a GUI that is most effective for this particular project So I can create the most user friendly interface possible while not effecting the integrity of the game. | a) Unanimous agreement on GUI. | Options include : netbeans, java swing, etc | Sprint 1 | Accepted | 1 | Rachel | 2017-03-14
Making the game | MTG2 | As the game user I want to have a game screen So I can have a visual while playing the game | a) Acceptable graphics | Bonus: Moving pieces | Sprint 1 | Accepted | 8 | Rachel | 2017-03-14
Making the game | MTG3 | As the game user I want to have an ending screen So I can see who won and possibly restart | a) Create acceptable graphics and possible restart button |  | Sprint 1 | Accepted | 3 | Allison | 2017-03-20
Sprint start: | 2017-03-12 |  |  |  |  | Total Points Sprint 1: | 49
Sprint Due: | 2017-03-21 |  |  |  |  | Points Complete: | 49
[6 empty] | Allison's Sprint 1 TODO Points | 14
[6 empty] | Rachel's Sprint 1 TODO Points | 13
[6 empty] | Kerry's Sprint 1 TODO Points | 17
[6 empty] | All 3 Sprint 1 TODO | 5

## Sprint 2
Mancala Sprint 2
Theme | ID | User Story | Acceptance Criteria | Comments | Sprint | Status | Points | Completed | Date Finished
Making the game | MTG5 | Have smooth player interaction | a) Working functionality within the game | Fix the seed stacking, Possibly random | Sprint 2 | Accepted | 3 | Rachel | 2017-03-26
Making the game | MTG11 | Limit where a player can click | a) Create a boolean to represent player one or two, player score, bool to check turns. | Boolean values represent the player turns and object contains each players score. | Sprint 2 | Accepted | 1.0 | Allison | 2017-03-25
Making the game | MTG12 | Create a function for the player to move pieces | a) Make player call move function in data structure | Done on early sprint 1, 0 points towards sprint 2 | Sprint 2 | Accepted | 5 | Done (Kerry) | 2017-03-19
Making the game | MTG13 | Create a turn indicator | a) Create acceptable graphics that indicate which players turn it is during the game. | Could be a banner, a symbol, etc. | Sprint 2 | Accepted | 2.0 | Rachel | 2017-03-26
Making the game | MTG16 | Vary number of seeds in hole & random distribution of seeds | Player one and player two should mirror eachother |  | Sprint 2 | Accepted | 2 | Kerry | 2017-03-22
Making the Game | MTG17 | Implement a time limit | if player does not make move within time limit, they lose |  | Sprint 2 | Accepted | 3 | Rachel | 2017-03-28
Making the game | MTG18 | Implement "Pie Rule" | only happens on second move, follows class document |  | Sprint 2 | Accepted | 4 | Kerry | 2017-03-22
Making the game | MTG19 | Edit Start for input on variable game hole | Allows user to input how many holes they want |  | Sprint 2 | Accepted | 3 | Allison | 2017-03-24
Making the game | MTG20 | Edit game Screen for variable game holes | Draws the gameScreen according to user input |  | Sprint 2 | Accepted | 1 | Rachel | 2017-03-26
Making the game | MTG21 | Variable game board holes | Edits the board class accoring to user input |  | Sprint 2 | Accepted | 3 | Kerry | 2017-03-26
Making the game | MTG22 | Insert ending screen into game screen | Shows a more accurate ending screen |  | Sprint 2 | Accepted | 4 | Allison/Rachel | 2017-03-30
Creating AI | CRA3 | Implement a minimax tree | a) Pass unit tests. |  | Sprint 2 | Accepted | 7.0 | Kerry | 2017-03-27
Creating AI | CRA7 | Implement the utility function | Accurately depicts what is described in class slides | See Slides | Sprint 2 | Accepted | 4.0 | Kerry | 2017-03-27
Creating AI | CRA8 | Implement alpha beta data pruning on one level | a) Make sure the degrees of the parent is less after pruning and make sure it prunes non optimal local moves. |  |  | NOTE: discovered during this sprint that one level pruning is not necessary. Will work on multilevel pruning next spint | 0
Creating AI | CRA10 | Create unit tests | a) Make sure DFS returns correct path, make sure AI has all possible moves, make sure pruning works, make sure computer selects optimal move |  | Sprint 2 | Accepted | 6.0 | Kerry,Rachel | 2017-03-30
Creating AI | CRA11 | Keep up code styling, comments and documentation for AI | a) Doxygen files, consistent naming/commenting. |  | Sprint 2 | Accepted | 4.0 | All | 2017-03-30
Client Serve Model | CS17 | Make a Basic Client server Model to that we can build on throughout the project | Simulates the one in class with more functionality according to our needs |  | Sprint 2 | Accepted | 3 | Rachel | 2017-03-27
Client Server Model | CS14 | Make a timing function | a) Research a timing library to use. |  | Sprint 2 | Accepted | 1.0 | Rachel | 2017-03-26
Other | OTH4 | As a team member I want to have a team meeting outside of class for Sprint 2 So I can have continuous updates on the status of the project | a) Meet On 3/26/2017 |  | Sprint 2 | Accepted | 1.0 | All | 2017-03-26
Sprint start: | 2017-03-21 |  |  |  |  | Total Points Sprint 2: | 57
Sprint Due: | 2017-03-30 |  |  |  |  | Points Complete: | 57
[6 empty] | Allison's Points | 6
[6 empty] | Rachel's Points | 18
[6 empty] | Kerry's Points | 23
[6 empty] | All 3 TODO | 5
[6 empty] | Already done | 5

## Sprint 3
Mancala Sprint 3
Theme | ID | User Story | Acceptance Criteria | Comments | Sprint | Status | Points | Assigned | Date Finished
Creating AI | CRA9 | Implement alpha beta data pruning on multiple levels Low priority | a) Make sure the degrees of the parent is less after pruning and make sure it prunes non optimal global moves. | Low priority job | Sprint 3 | To do | 5 | Kerry | 2017-04-05
Client Server Model | CS15 | keep up code styling, comments and documentation for the network | a) Doxygen files, consistent naming/commenting. | Also get rid of warnings | Sprint 3 | To do | 4.0 | All | 2017-04-09
Other | OTH1 | Write Group Report | a) Follows MLA format and instructions. |  | Sprint 3 | To do | 1.0 | All | 2017-04-09
Other | OTH5 | have a team meeting outside of class for Sprint 3 | a) Meet 4/2/2017 |  | Sprint 3 | To do | 1.0 | All | 2017-04-04
Additions | ADD1 | create pi rule button on game screen | pi rule button correctly shows pi rule | Put button on screen, connect to pi rule to redraw screen | Sprint 3 | To do | 3 | Allison | 2017-04-07
Additions | ADD2 | enhance graphics | lowest priority, make it look cool | fix end screen, add to game screen & beginning screen | Sprint 3 | To do | 2 | Rachel/Allison
Additions | ADD3 | put in all options for games | options accurately create board as needed, random seeds | How many holes per side, seed arrangements(random or not), timer setting(on/off, if on how long), play person to person, person to computer or computer to computer | Sprint 3 | To do | 7 | Allison | 2017-04-08
Additions | ADD4 | implement random seeding | seeds are distributed in a "random" fashion on board start | random number [4,9] | Sprint 3 | To do | 2 | Allison/Kerry | 2017-04-04
Additions | ADD6 | Implement all server functions | pass testing | follow given "changes" document | Sprint 3 | To do | 10 | Kerry | 2017-04-09
Additions | ADD7 | implement all client functions | pass testing | follow given "changes" document | Sprint 3 | To do | 10 | Rachel | 2017-04-09
Additions | ADD8 | connect AI to server | can create an AI player through server |  | Sprint 3 | To do | 5 | Kerry | 2017-04-09
Additions | ADD9 | Have AI recognize pi rule | pass unit tests |  | Sprint 3 | To do | 3 | Kerry | 2017-04-07
Additions | ADD10 | minor bug fixes | All bugs on the "bug list" are fixed | add to the list / take away as needed | Sprint 3 | To do | 4 | All | 2017-04-09
Sprint start: | 2017-03-31 |  |  |  |  | Total Points Sprint 2: | 57
Sprint Due: | 2017-04-09 |  |  |  |  | Points Complete: | 57
[5 empty] | Allison's Points | 14
[5 empty] | Rachel's Points | 13
[5 empty] | Kerry's Points | 16
[5 empty] | All 3 TODO | 10